## Slide 1
2016
2017
Today
Sep
Oct
Nov
Dec
2017
Feb
Mar
Apr
Introduction to SRD and Capstone
9/9/2016
Proposal
11/18/2016
Capstone Project Implementation
11/25/2016
SRD Research Report
4/7/2017
Capstone Presentation
4/10/2017
10 days
Selection of Research Topic/Issue
9/5/2016 - 9/16/2016
11 days
Compilation of Initial Research List
9/16/2016 - 9/30/2016
6 days
Identification of Gaps in Learning
9/16/2016 - 9/23/2016
10 days
Selection of Advisor or Mentor
9/19/2016 - 9/30/2016
6 days
Formulation of SMART GOALS
10/3/2016 - 10/10/2016
9 days
Mapping of SMART GOALS to Timeline
10/11/2016 - 10/21/2016
20 days
Execution of Project Proposal
10/24/2016 - 11/18/2016
5 days
Outline
11/28/2016 - 12/2/2016
10 days
Literature Review & Introduction
12/5/2016 - 12/16/2016
10 days
Materials & Methods
12/5/2016 - 12/16/2016
15 days
12/17/2016 - 1/6/2017
Draft I
20 days
Results (Collection & Format)
1/7/2017 - 2/3/2017
15 days
Discussion & Analysis of Results
2/4/2017 - 2/24/2017
10 days
Conclusion
2/20/2017 - 3/4/2017
6 days
Abstract
3/6/2017 - 3/13/2017
5 days
Peer Review
3/14/2017 - 3/20/2017
5 days
Draft II
3/21/2017 - 3/27/2017
9 days
Final Paper Due
3/28/2017 - 4/7/2017
66 days
11/25/2016 - 2/24/2017
Capstone [Project Implementation/Portfolio/Experimentation]
6 days
Creating a Final Presentation
4/10/2017 - 4/17/2017
5 days
Preparing Final Presentation
4/17/2017 - 4/21/2017
5 days
Final Capstone Presentations
4/24/2017 - 4/28/2017